## Slide 1
Presentation to the
Mission Valley Design Advisory Board
February 5, 2018
Project Summary
Phase 2 Solar Installations at City Facilities
City of San Diego
Sustainability Department
Doran Aivati and James Chen
Presentation to the
Sustainable Energy Advisory Board
August 8, 2019

## Slide 2: Description & Goals
Brief description of the work:
Creating our own RFP in house for Solar; will go to the “short list” of vendors identified in the RFSQ
A total of 4 sites. Estimated total of 1.165 MW solar panels to be installed
ESD Miramar Place, Canyonside Rec Center, North UTC Library and Nobel Rec Center, Allied Garden Rec Center & Pool
Goals
The City’s proposed Climate Action Plan goal of 100% Renewable Energy citywide by 2035
Installation of renewable energy supports the City’s Climate Action Plan and sustainability goals and GHG reduction
Partners or vendors and brief description of their roles:
Kitchell, RFP Consultant
Shortlisted Vendors for Solar RFQ
  1. Borrego Solar System, Inc.
  2. NextEra Energy Resources, LLC
  3. OpTerra Energy Services, Inc.
  4. SolarCity Corporation DBA Tesla Energy
  5. SunPower Corporation, System

## Slide 3: Budget & Timeline
Budget and/or description of funding:
No budget or up front costs. The City will sign a “Power Purchase Agreement” (PPA) with the selected vendor for a term of 20-25 years at a fixed rate for each site
Timeline and/or contract term:
RFP currently under City Attorney review. Planned to be completed and ready to be put out to bid by 9/15/2019
RFP Vendor chosen by 10/15/2019
Start Construction by 12/01/2019
Complete Construction by 5/30/2020
Term of executed PPA will be 20-25 years

## Slide 4: Issues & Future Risks
Potential Issues During Planning and Construction:
Community engagement pending
Restore parking lot and landscape conditions after the completion of construction
Future Risks:
Financial break-even unknown; TOU rates complicate the value proposition for PPAs
  Will be assessed during procurement process
  Working with Rocky Mountain Institute to develop a financial model to calculate pay back